## Slide 1: Parking Assistant

## Slide 2: Project content:
What’s parking assistant?
Project scope.
Project WBS.
Responsibility matrix.
Project network.
Gantt chart.
Resource-constrained schedule.
Cumulative baseline budget.
Benefits of the project.
Risks.

## Slide 3: What’s parking assistant?
World is constantly increasing so finding a parking lot is no longer so easy.
We faced this problem by our project that will help drivers to find a parking easily and we will finish this project in one year.
Our project is an introducing a solution for the parking spaces problem by building a lot of parking both in multiple floors or underground ,creating an app that helps people find an empty parking spaces ,and pay attention to the streets and infrastructure of crowded cities.

## Slide 4: Project scope:
The project helps drivers to get an easy parking.
Project in general:
The project provides an easy and safe parking for drivers by an application that is connected with a sensors in the building which detected the free parking spaces in the building.
The drivers can deal with the application easily.
Project constraints:
The project should be available in one year of the project intiation.
The cost is only 1.53 million dollars.
We have just three teams: Architect, civil engineering, and software engineering team.
Project exclusions:
Drivers are not able to reserve a parking space.
There is no car service in the building.

## Slide 5: Project WBS:
Parking assistant
Building
Application
System
-Designing the building.
-Importing the IR sensors and security cams from a factory.
-Drawing the parking spaces in each floor.
-Placing the IR sensors in specific places.
-Designing the application.
-Encoding the application
-Connecting the application with the building.
-Launching the application to the public.

## Slide 6: Responsibility matrix:
Tasks | Abdelaziz | Arwa | Aysel | Rawan | Gaser | Ahmed | Omar | Oday | Rana | Selim
Project planning | R I | A | C | R I | C | C | A | C | C | A
Meeting protocols | C | R | A | I | C |  |  |  |  | 
Building design |  |  |  |  | C |  |  |  |  | R
Importing IR sensors and security cams |  |  |  |  | C | R | A | I | I | 
Drawing the spaces |  |  |  |  | C |  |  |  | R | 
Placing the sensors |  |  |  |  | C |  |  |  | R | 
App design |  |  |  |  | C | R | A | I | I | 
App encoding |  |  |  |  | C | R | A | I | I | 
Connecting the app with the building |  |  | C | A | C | R | A | I | I | 
Launching the app |  |  | C | A | C | R | A | I | I | 

## Slide 7: Project network:
30 | A | 0
Project planning |  | 0
30 | 30 | 0
45 | B | 30
Building design |  | 0
45 | 15 | 30
90 | C | 45
Importing sensors and cams |  | 0
90 | 45 | 45
30 | D | 90
Drawing spaces |  | 0
105 | 15 | 90
135 | E | 105
Placing the sensors |  | 0
135 | 30 | 105
75 | F | 45
App designing |  | 30
105 | 30 | 75
105 | G | 75
Encoding the app |  | 30
135 | 30 | 105
180 | H | 135
Connecting the app with the building |  | 0
180 | 45 | 135
195 | I | 180
Launching the app |  | 0
195 | 15 | 180
Critical path:
A, B, C, D, E, H, I

## Slide 8: Gantt chart:
0 15 30 45 60 75 90 105 120 135 150 165 180 195 210
A
B
C
D
E
F
G
H
I

## Slide 9: Resource-constrained schedule:
ID | RES | ES | LF | DUR | SL |  |  |  |  |  |  |  |  |  |  |  |  | 
A | 10 | 0 | 30 | 30 | 0 | 10 | 10 |  |  |  |  |  |  |  |  |  |  | 
B | 2 | 30 | 45 | 15 | 0 |  |  | 2 |  |  |  |  |  |  |  |  |  | 
C | 5 | 45 | 90 | 45 | 0 |  |  |  | 5 | 5 | 5 |  |  |  |  |  |  | 
D | 2 | 90 | 105 | 15 | 0 |  |  |  |  |  |  | 2 |  |  |  |  |  | 
E | 2 | 105 | 135 | 30 | 0 |  |  |  |  |  |  |  | 2 | 2 |  |  |  | 
F | 5 | 45 | 105 | 30 | 30 |  |  |  | 5 | 5 |  |  |  |  |  |  |  | 
G | 5 | 75 | 135 | 30 | 30 |  |  |  |  |  | 5 | 5 |  |  |  |  |  | 
H | 7 | 135 | 180 | 45 | 0 |  |  |  |  |  |  |  |  |  | 7 | 7 | 7 | 
I | 7 | 180 | 195 | 15 | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 7
Total resources |  |  |  |  |  | 10 | 10 | 2 | 10 | 10 | 10 | 7 | 7 | 7 | 7 | 7 | 7 | 7
Reference |  |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
0 0.5 1 1.5 2 2.5 3 3.5 4 4.5 5 5.5 6 6.5

## Slide 10: Time-phased budget: ($000)
ID | Activity name | DUR | BD |  |  |  |  |  |  |  |  |  |  |  |  | 
A | Project plan | 30 | 400 | 200 | 200 |  |  |  |  |  |  |  |  |  |  | 
B | Building design | 15 | 500 |  |  | 500 |  |  |  |  |  |  |  |  |  | 
C | Importing sensors & cams | 45 | 30 |  |  |  | 10 | 10 | 10 |  |  |  |  |  |  | 
D | Drawing spaces | 15 | 30 |  |  |  |  |  |  | 30 |  |  |  |  |  | 
E | Placing sensors & cams | 30 | 70 |  |  |  |  |  |  |  | 30 | 40 |  |  |  | 
F | App designing | 30 | 300 |  |  |  | 150 | 150 |  |  |  |  |  |  |  | 
G | App encoding | 30 | 100 |  |  |  |  |  | 50 | 50 |  |  |  |  |  | 
H | Connecting between the app & the building | 45 | 80 |  |  |  |  |  |  |  |  |  |  |  | 80 | 
I | Launching the app | 15 | 20 |  |  |  |  |  |  |  |  |  |  |  |  | 20
Total budget in half month |  |  | 1530 | 200 | 200 | 500 | 160 | 160 | 60 | 80 | 30 | 40 | 0 | 0 | 80 | 20
Cumulative |  |  |  | 200 | 400 | 900 | 1060 | 1220 | 1280 | 1360 | 1390 | 1430 | 1430 | 1430 | 1510 | 1530
0 0.5 1 1.5 2 2.5 3 3.5 4 4.5 5 5.5 6 6.5

## Slide 11: Cumulative baseline budget:
Chart: 
| 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7
Y-Values | 0.2 | 0.4 | 0.9 | 1.06 | 1.22 | 1.28 | 1.36 | 1.39 | 1.43 | 1.43 | 1.43 | 1.51 | 1.53
Budget ($000000)
Month

## Slide 12: Benefits of the project:
Building a lot of parking both in multiple floors or underground that will increase the parking spaces.
Creating an app that helps people find an empty car park easily.
Paying attention to the streets and infrastructure of crowded cities.

## Slide 13: Risks:
-Here are some potential risks and how to deal with them:
1-A problems with the geographical location:
There may be a problem with the geographical location, to avoid it, the site must be examined by the architect before completing the building design.
2-Lack of drivers who have the ability to use the application:
In order to face this problem, we have allocated a month to train the drivers to understand how to use the application. Any driver can subscribe during this month and within a three days he will be able to use the application well.

## Slide 14
3-Hacking the system by unethical hacker:
This would be a big trouble, so we assigned a software engineer who is responsible for securing the system and making it safe against hacking.
4-Sudden failure or fracture of any sensor:
To solve this problem, we contact the company sponsoring the project to provide us with a responsible person to solve this problems with sensors.